## Slide 1: City & Hackney Annual Plan 2022-23

## Slide 2
Staff Wellbeing
Workforce, Equality and Diversity
Integrated Care, Partnerships & Coproduction
Service User Outcomes
Waste reduction
Sustainability
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
To improve the quality of life for all we serve
Strategic Objectives
Secondary Drivers
22-23 Priorities
Equality and Diversity - address gaps around access and outcomes for socio-economic, health and diversity issues for staff and service users
New Service Developments
Engaging with new integrated care systems - become a full partner in the new structures and how we relate to different Trusts
Co-production: skills capabilities, leadership and capabilities
Mental Health Community Transformation - Establishing PCN and 8 neighbourhood teams and borough wide complex care teams
Future of Inpatient Services work - realignment of bed capacity to community transformation, inpatient recovery work to improve quality of care
Shaping future services - managing ongoing challenges, develop service models to accommodate digital and face to face, WFH, organise services
Staff Well-being and Retention
Review models of care and treatment
Rehab service (financial viability) - financial viability proposal exploring the feasibility of a NEL rehabilitation pathway
Infrastructure to support: tools, skills and staff capabilities
Review of Hackney dementia service - make necessary improvements to the pathway and manage backlog waiting list
East London Neurological Pathway - creation of an East London wide neurological service for ADHD ASD
Delivery of LBH savings plan - develop a new model of supported accommodation in Hackney
Perinatal Mental Health service development – develop a clear perinatal service model strategy

## Slide 3
City & Hackney Annual Plan Priorities 22-23
Priority | Actions | Ownership | Challenges | Timelines | Support required (internal) | Support required (external)
Staff Well-being and Retention | Developing a clear plan for staff: - Complete staff engagement – focus groups Review how team working models to be renewed in light of changes Access to training and supervision Manageable workloads, Improving communication to address issues highlighted Recruitment and retention, developing jobs and making things attractive, flexible , being creative using social media (tik tok etc) Staff development, career progression (nursing, social work, OT) – clear offer for progression Career progression for registered & unregistered staff (CPD) Contracts and employment review Addressing inequalities and staff wellbeing | Tolu/Business Partner | Too much, vacancies and cover challenges, morale , staff feel they are being heard Having breaks, caseload management, wellbeing, reflective session, breaks and going home on time | 12 months | Setup focus group to engage with staff | OD, Training and Development, P&C
East London Neurological Pathway - creation of an East London wide neurological service for ADHD ASD | To complete scoping of service model exercise to agree pathways Engage with TH and NH Review current models Identify future models with staff Agree care models and pathways and operationalise offer, particularly around PCN Recruitment Develop proposal for future model and Agree funding model with CCGs/ICS. Review collective spend . | Olivier/Andrew | Increase in demand, investment gaps, capacity challenges, nurse prescribing training takes 2 years. PCNs are taking on these cases adding to workload. | 6-12 months |  | 
Review of Hackney dementia service - make necessary improvements to the pathway and manage backlog waiting list | Review with Dementia Alliance and agree a plan. Finalise NHSE review and SSNAP findings Review capacity to address backlog | Cath/Waleed |  | 6-12 months | work with local project support | Waleed/ Trustwide review with other MHCOP services

## Slide 4
City & Hackney Annual Plan Priorities 22-23
Priority | Actions | Ownership | Challenges | Timelines | Support required (internal) | Support required (external)
Delivery of LBH savings plan - develop a new model of supported accommodation in Hackney | Progressing current plans to review contracts, reduce high cost spot purchases Reviewing caseload and moving on users Review care packages Prioritising Dom care and high cost spend Associated costs (Blitz clean and storage and kennels ) Looking at housing with care, shared lives provision Wider discussions with LA about provision (housing quota) Ensuring mental health care provision (s117) Supporting users to manage tenancies with VSC | Andrew |  | 6-12 months |  | Local Authority /VSC
Future of Inpatient Services work - realignment of bed capacity to community transformation, inpatient recovery work to improve quality of care | Review how well current change ideas are working across the directorate. (take stock) Strengthening community pathway and capacity Reviewing expectations around care planning and offers (CPA, DIALOG) Making neighbourhood models set up and how to access the offer Improving quality of care – Restrictive care Review/evaluate discharge team impact Addressing variation in practices | Victoria/Becks/Cath/Andrew |  | 6-12 months | Developing dedicated project capacity (Dean) | David bridle/Paul G, supporting consultants
Perinatal Mental Health Service Development - develop a clear perinatal service model strategy, meet national targets and deliver on investment standards | Review with Justine | Justine |  |  |  | 

## Slide 5
City & Hackney Annual Plan Priorities 22-23
Priority | Actions | Ownership | Challenges | Timelines | Support required (internal) | Support required (external)
Mental Health Community Transformation - Establishing PCN and 8 neighbourhood teams and borough wide complex care teams | Review of the neighbourhoods, system workforce, processes. -Implementation in place Work on complex needs Older Adults Developing assessment service Aligning services to neighbourhoods Work on RIO changes, clinical system Older Adult interface o EI pathway closer to team o Perinatal pre-conception advice o Crisis services - Enhanced FACT model o Social care TBC Plan is to integrate teams to encompass all the functions – ie CPA, OP, Rehab, Crisis. Currently not very joined up | Nicola |  | 18 months | PMO in place | Estates, Digital
Shaping future services - managing ongoing challenges, develop ervice models to accommodate digital and face to face, WFH, organise services | Define scope of priority Understand what is available (platforms, training etc) identify resources and timeframes Analyse clinical impact of platforms tested Develop directorate approach | TS & MM | Who is driving this? Clarity on preferred platforms | Scoping phase: 3m Phased implementation: 9m | Clinicians | Digital Team Dialog Team
Infrastructure to support: tools, skills and staff capabilities | Connected to above |  |  | Scoping phase: 3m |  | 
Engaging with new integrated care systems - become a full partner in the new structures and how we relate to different Trusts | Define scope of priority Break down into components and agree where to focus effort | NG + DH + OA | Navigating new ICS landscape | Scoping phase: 3m |  | System partners

## Slide 6
City & Hackney Annual Plan Priorities 22-23
Priority | Actions | Ownership | Challenges | Timelines | Support required (internal) | Support required (external)
Developing place-based integrated care, neighbourhood model across Hackney - partnering across primary, secondary and specialist services | Define scope of priority Review of Neighbourhood Implementing necessary changes Delivering on national transformation priorities | NG + AH + CM | CPA change Transition from current recovery teams to neighbourhood model | Scoping phase: 3m | Community Staff | Central Neighbourhood Group
Equality and Diversity - address gaps around access and outcomes for socio-economic, health and diversity issues for staff and service users | Define scope of priority Identify gaps | TO + | Many factors/complex | Scoping phase: 3m | Performance People & Culture Staff Side | 
Rehab service (financial viability) - financial viability proposal exploring the feasibility of a NEL rehabilitation pathway |  | SA & LH |  | Scoping phase: 3m |  | 
Review models of care and treatment | Define scope of priority | CM + AH + BR |  | Scoping phase: 3m |  | 
Co-production: skills capabilities, leadership and capabilities |  | HM + OA +DH |  | Scoping phase: 3m |  |