## Slide 1: Commercial Development Annual Plan 2022-23
March 2022

## Slide 2
Staff Wellbeing
Communication
ICS and System Working
Resource and Skill Set
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
To improve the quality of life for all we serve
Strategic Objectives
Secondary Drivers
22-23 Priorities
Impact on CDD
Address duplication of work through consolidation of tasks and leads for projects
SOP for different roles and function to allow clarity of purpose – links o ICS/DMT on what they want
Update work plans, contract register and meeting structure around new ways of working. Devise optimum structure
Workshop with ICS programme director for ELFT to think through CDD offer and links to wider system to have clarity of purpose on role within ICS.
Regular update to DMTs on CDD support – what we need from them and what they can get from us (monthly contract, procurement, BD update)
Updates on CDD development via Intranet, Trust talk etc.
Dedicated DMT and corporate leads/clear communication across networks to ensure better partnership working between CDD and DMT
Liaise with different stakeholders – internal/external to align our understanding and impact on each function including alliances, VCSEs, corporate teams, DMTs – all staff involved
Links to ICS development meeting in EL and BLMK
Regular Updates on ICS development - internally
Maintain work life balance through hybrid working
Training and development for new ways of working (new skills, expertise and experience)
Lunch and learns like Primary Care (CMHT Transformation, ICS)
Opportunities to reflect e.g. weekly catch ups and shared learning from training
Inter Trust support and expertise – opportunities for learning, shared systems and resources
Shadowing opportunities
Support tenders that don’t directly benefit ELFT
Spending better – support Anchor
VCSE asset mapping
OD – insights/colours – new ways of working – One page profile
Decision making principles for commissioning and contracting (ICS agreed(
Does CDD support internal business cases? E.g. FV

## Slide 3
Commercial Development Plan Priorities 22-23
Key Priority Area | Strategic Priority | Milestones | Local Leads | Challenges | Internal Support Required | External/Corporate Support Required | Expected Delivery Dates + Timelines | Scale | Status
Staff Wellbeing | Staff experience | OD – insights / colours – new ways of working | Robin Campbell / Tom Morgan | Await new ADs | None | P&C OD support | Jul-22 | Trustwide | in progress
 | Staff experience | Maintain work life balance through hybrid working | Line Managers | N/A | N/A | N/A | Q1 | Trustwide | completed
 | Staff experience | Lunch and learns like Primary Care (e.g.CMHT transformation, ICS) | Daniel Efunnuga | Getting regular speakers | PM support | Various | Q2 | Trustwide | in progress
 | Staff experience | Share learning from training, CPD | Robin Campbell / Tom Morgan | Planning in advance to prepare | PM support | None | Q1 | Trustwide | in progress
Resource and Skill Set | Staff experience | Inter Trust support and expertise – opportunities for learning, shared systems and resources | Steph/Christian/ Procurement Band 7 | N/A | None | Links to collabortives, peer suportgroups | Q1 | Trustwide | in progress
 | Staff experience | Training and development for new ways of working (new skills, expertise and experience) | Line management / Leads / Linked to lunch and learn Need to do a gap analysis | Training available | None | Internal training in ICS / external training | Q1-Q2 as part of appraisal | Trustwide | in progress
 | Staff experience | Shadowing opportunities | Line management/Leads | Availability | None | Various | Q1-Q2 as part of appraisal | Trustwide | in progress
ELFTs Position in the ICS / System Working | Value | Spending better – supporting Anchor - developing social value metrics and systems | Procurement | Data quality | Routine monitoring | Agreeing routine metrics | Q1 - Q3 | Trustwide | in progress
 | Population health | Support tenders that don’t directly benefit ELFT | Steph/Alicia/Daniel | Appetite for joined up working | None | Links with VCSE / ICS - agreement of approach with Mohit | Q2 - Need to discuss with Mohit | Trustwide | in progress
 | Value | Does CDD support internal business cases? E.g. FV | Robin/Mohit | Prioritisation over external | None | Agree approach with Mohit | Q1 | Trustwide | in progress
 | ALL | Decision making principles for commissioning and contracting (ICS agreed) | Robin | N/A | N/A | N/A | Q1 | Trustwide | completed
 | Population Health | VCSE asset mapping | Alicia | Access to info | None | Integrated care, population health | Q1 | Trustwide | in progress

## Slide 4
Commercial Development Plan Priorities 22-23
Key Priority Area | Strategic Priority | Milestones | Local Leads | Challenges | Internal Support Required | External/Corporate Support Required | Expected Delivery Dates + Timelines | Scale | Status
Communication | ALL | Workshop with ICS programme director for ELFT to think through CDD offer and links to wider system to have clarity of purpose on role within ICS | Robin/Sam | N/A | N/A | N/A | n/a | Trustwide | completed
 | ALL | Dedicated DMT and corporate leads / clear communication across networks to ensure better partnership working between CDD and DMT | Tom/Robin/Steph/Christian | Engagement | DMT leads | DMTs / development of a process | Q1 | Trustwide | in progress
 | ALL | Regular update to DMTs on CDD support – what we need from them and what they can get from us (monthly contract, procurement, BD update) | Tom/Robin/Steph/Christian | Engagement | DMT leads | DMTs / development of a process | Q1 | Trustwide | in progress
 | Staff Experience | Updates on CDD development via intranet, Trust talk etc | Tom / Robin / Steph / Christian | None | PM support | Comms Dept | Q3 | Trustwide | in progress
 | ALL | Liaise with different stakeholders – internal / external to align our understanding and impact on each function including alliances, VCSEs, corporate teams, DMTs – all staff involved | Sam / Robin / Steph / Christian | Engagement | DMT leads | DMTs / development of a process | Q1 - DMT Workshop, ICS Workshops | Trustwide | in progress
 | Value, Staff Experience | Links to ICS development meeting in EL and BLMK | Robin/Tom | Engagement | None | Integrated care | Ongoing | Trustwide | in progress
 | ALL | Regular updates on ICS development - internally | Robin / Tom - CDD monthly | Engagement | None | Integrated care | Ongoing (Quarterly update) | Trustwide | in progress
Impact on CDD | Value, Staff Experience | Address duplication of work through consolidation of tasks and leads for projects | Steph/Christian/Procurement Band 7 / Tom /Robin | Sourcing right systems, prioritising process review over BAU | Leads and allocated capacity to review | Qi, digital, finance | Ongoing via contract procurement meetings - Q2-Q4 | Trustwide | in progress
 | Staff Experience/ Value | SOP for different roles and function to allow clarity of purpose – links to ICS / DMT on what they want | Leads | Defining roles acorss the organsation in the new ICS | Team leads | DMTs, Integrated care | Link to DMT development - Q2-Q3 | Trustwide | in progress
 | Staff Experience/ Value | Update work plans, contract register and meeting structure around new ways of working. Devise optimum structure | Christian | N/A | N/A | N/A | Completed | Trustwide | completed

## Slide 5
Commercial Development Plan Priorities 22-23
Key Priority Area | Strategic Priority | Milestones | Local Leads | Challenges | Internal Support Required | External/Corporate Support Required | Expected Delivery Dates + Timelines | Scale | Status
Support system planning through the development of Integrated Care Systems through new contract arrangements and governance systems |  | Subject to national guidance on the new operating model CDD will be required to support the development of new contractual arrangements and governance systems . | Tom and contract leads | Number of changes in contract approaches. Multiple SLA and contracts acrss collabortievs and partnerships | Contract team | DMTs/Finance/Informatics/Performance/Estates/ Integrated Care Systems stakeholders (joint working) | Ongoing throughout 2022/23 | Trustwide | in progress