## Slide 1: Estates Annual Plan 2022-23
March 2022

## Slide 2
New Service Developments
Integrated Care, Partnerships and Coproduction
Estates
Sustainability
Bids, Contracts and Commissioning
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
To improve the quality of life for all we serve
Strategic Objectives
Secondary Drivers
22-23 Priorities
Bedford Health Village – New Inpatient Facility
Moving out of Passmore Edwards to first avenue
Local Service Transformation work
Imbed new Soft FM service provider
Property and asset condition review, including accessibility and space utilisation
Creation of Estates Strategic Operating Framework
Sale of properties in London Road, Lewsey Road and sale and leaseback of properties to HCSN
Single Mile End site – One borough inpatient site (Hackney and Tower Hamlets) MHCOP Centre of Excellence
Develop clear estate strategy for Pharmacy
Capital Plans development
Creation and Implementation of Trust’s Green Plan
Business case to expand single user facility in Moorgate Ward
Review of estates incident management process
GP request to occupy additional space within Health Centres
Review estates partnership arrangement with HCSN
Estates net zero plan – pioneering decarbonisation pilot programme at Beech Close Resource Centre to fully decarbonise existing site
Identify sites for onsite energy generation
Identifying potential for combined energy purchasing or combined renewables
Increase recycling provision to 70% of sites
Initiate reuse scheme
Locate sites for NHS forest

## Slide 3
Estates Annual Plan Priorities 22-23
Key Priority Area | Strategic Priority (staff experience/population health/value/experience of care) | Milestones | Local Leads | Challenges | Internal Support Required | External/Corporate Support Required | Expected Delivery Dates + Timelines | Scale | Status | Comments
Bedford Health Village - New Inpatient Facility | Experience of Care | Indicative Milestones: Feasibility Study Complete: March 2022 Strategic Outline Case Approved: July 2022 Outline Business Case Approved: Dec 2022 Full Business Case Approved: April 2023 Construction Commences: May 2023 Facility Opens : December 2024 | Eugene Jones/Richard Fradgley | 1. Funding. 2. Appointment of Senior Estates Project Manager by end 22 |  | Finance, Executive Decision | Dec-24 | Trustwide | in progress | Feasibility design team appointed. Workshops and site visits commenced
Moving out of Passmore Edwards to First Avenue | Staff Experience | Scheme Currently working progress | Bailey Mitchell | 1. HCSN - Feasibility study and associated delays |  | Finance, Executive Decision | 18 months | Local/Place-based | On Hold | This scheme has been paused at Tender stage until the HCSN development feasibility report for the whole First Avenue site is considered.
Capital Plans Development | Value | 1. Clarify successful bids and investment envelope (Create 5 year Capital Plan) 2. Agree priority projects and schemes. 3. Improved CPSG and FBIC reporting. 4. Establish Estates / Digital Capital Board. 5. Appointment of PMO/PSO support. | Mark Taylor/ Borough Directors | 1. Available resource 2. Inadequate CEDEL |  | Finance, Executive Decision | 12 months | Local/Place-based | in progress | A number of schemes have been delivered and the remaining capital programme is currently being re-profiled to match the agreed CDEL

## Slide 4
Estates Annual Plan Priorities 22-23
Key Priority Area | Strategic Priority (staff experience/population health/value/experience of care) | Milestones | Local Leads | Challenges | Internal Support Required | External/Corporate Support Required | Expected Delivery Dates + Timelines | Scale | Status | Comments
Single Mile End Site – One Borough inpatient site (Hackney and Tower Hamlet’s) MHCOP Centre of Excellence | Value | Scheme yet to be confirmed – transformation project leads currently scoping | Richard Fradgley | 1. Barts Masterplan |  | Finance, Executive Decision | 5 years | Trustwide | in progress | Barts have set up a meeting to dicuss their MileEnd masterplan for March 23
Pharmacy | Value | Develop clear estate strategy for one storage solution, or multiple sites to manage increased demand -Looking for premises -Commercial Appraisal of options, Financial viability on selling medication to other providers | Jenny Melville /Amy King |  |  | Finance, Pharmacy, CDD, Executives Decision, Digital, Corporate Nursing | 3- 6 month (decision on approach) | Trustwide | On Hold | The relocation of Pharmacy is on hold until a business investment plan is completed.
Business case to expand single user facility in Moorgate Ward | Population Health | Increase ward to 4-5 medium secure wards Agree Business Case | Phil Baker / Sarah Barnett |  |  | CDD, Finance, Tony Lawford, Estates | 12 months | Local/Place-based | completed | Completed. Sketch design and cost plan produced submitted to local leads. C£3.7M There is insufficient funds / financial viability at this stage
Local Service Transformation Work | Staff Experience | Various service level initiatives under way such as Community Transformation Service redesign | Borough Directors Supported by K.Giles/L.Bedward/S.James |  |  | DMT’s | 12 months | Local/Place-based | in progress | Details for occupation is in progress. Updates at each DMT for Community & Estates meeting.

## Slide 5
Estates Annual Plan Priorities 22-23
Key Priority Area | Strategic Priority (staff experience/population health/value/experience of care) | Milestones | Local Leads | Challenges | Internal Support Required | External/Corporate Support Required | Expected Delivery Dates + Timelines | Scale | Status | Comments
Creation and Implementation of Trusts Green Plan | Population Health | 1. Creation of Green Plan. 2. Quarterly progress reports. 3. End of three year review date. | Adam Toll | 1. Funding to support NZC |  | Cooperation and input from all department leads | 12 to 36 months | Trustwide | completed | Green Plan was completed in Jan 22
Creation of Estates Strategic Operating Framework | Staff Experience | Creation of draft framework to guide estates in how it operates | David Stevens |  |  | None | Dec-21 | Trustwide | completed | 2021 / 2022 new priority
Refreshed Estates Strategy – current version expires Mid 2022 | All | Briefing Workshops. Scoping document for external advice. Appointment of external advice. Draft document | David Stevens / James Slaven / Exec |  |  | Cooperation and input from all department leads | 6 - 8 months | Trustwide | in progress | This will be completed in draft by August 22
Options analysis for John Howard Centre | Population Health | 1. Appointment of external team 2. Draft document issued | David Stevens / Phil Baker / Exec | Availability of Stakeholders | Frank Riedel | Borough Directors, Clinical Directors, Digital, Finance, Estates | Apr-22 | Trustwide | in progress | 
Identification and management of robust MI to enable effective data based decision making | Value | 1.Compliance reporting gap analysis and benchmarking. 2.Refocus on compliance and contractor performance management. 3.Improved contractor performance reporting including consistency and standardisation. 4. Dashboard development. 5. Creation of Estates Risk Register. 6. Appointment of Property & Contracts Manager. 7. Appointment of Senior Engineering & Maintenance Mgr | David Stevens / Karen Boreham / Frank Riedel | 1. Resource 2. Funding & Recruitment | Nick Webb Karen Boreham Shamima Alek | QI Team / Finance | 6 - 8 months | Trustwide | in progress | Interim Senior Engineer appointed Jan 22

## Slide 6
Estates Annual Plan Priorities 22-23
Key Priority Area | Strategic Priority (staff experience/population health/value/experience of care) | Milestones | Local Leads | Challenges | Internal Support Required | External/Corporate Support Required | Expected Delivery Dates + Timelines | Scale | Status | Comments
Property and Asset condition review, including accessibility and space utilisation | Value | Completion of 6 facet survey and creation of associated action plans and budgets. Refreshed Estates Strategy / Plan. Creation of Trust Masterplan (s), aligned to Clinical & Borough Strategy. Refocus of Capital & Asset Management Programme towards deliverability priority / reducing underspend. ‘Digital First’ focus and collaboration. | David Stevens / Adam Toll / Frank Riedel | 1. Resource 2. Recruitment 3. Retirement of Estates Adviser | Sonny James | Borough Directors, Clinical Directors, Digital, Finance, Estates | 12 months | Trustwide | in progress | 2021 / 2022 new priority
Estates Incident Management Processes | Staff Experience | Review of ERPP / IMP. Creation of estates specific content or documentation. Sign off by SDB. Imbedding of new processes. | David Stevens / Richard Harwin | 1. Time availability | Estates Leadership Team | Cooperation and input from all relevant department leads | Apr-22 | Trustwide | in progress | 2021 / 2022 new priority
Imbed new Soft FM Service Provider | Value | 1. Mobilise new Soft FM provider (Cleaning, Food, Pharmacy Shuttle, Escorting, etc - ELFT owned / managed sites only) 2. Imbed new Soft FM supplier | Kathy Giles / David Stevens | 1. Migration of data. 2. TUPE | Estates Facilities Team | Procurement / Contracts / Staff Side / HR / Primary Care | 01/04/2022 01/10/22 | Trustwide | in progress | Mobilisation will b comleted by 01/02/22. Imbedding will be imbedded by May 22
Sale of properties in London Road & Lewsey Road | Value | 1. Valuation of properties 2. Decision re Auction or Market Sale 3. Sale completion | David Stevens | 1. Market Appetite | John Brennan / Sonny James | Contracts / Finance | Apr-22 | Trustwide | in progress | 
Sale & Leaseback of properties to HCSN | Value | 1. Valuation of properties 2. Decision re viability (IFRS-16) 3. Sale completion | David Stevens | 1. Decision re viability (IFRS-16) | John Brennan / Sonny James | Contracts / Finance | Apr-22 | Trustwide | in progress | 

## Slide 7
Estates Annual Plan Priorities 22-23
Key Priority Area | Strategic Priority (staff experience/population health/value/experience of care) | Milestones | Local Leads | Challenges | Internal Support Required | External/Corporate Support Required | Expected Delivery Dates + Timelines | Scale | Status | Comments
GP request to occupy additional space within Health Centres | Experience of Care | 1. Confirmation of propsed locations 2. Funding Identification | Kathy Giles / Sonny James | 1. Relevant Funding | Marina Muirhead | CCG / ICB |  |  | in progress | 
Estates partnership arrangement with HCSN | Value | 1. Confidential till discussed within Estates | David Stevens |  | David Stevens | Finance | Jul-22 | Local/Place-based | in progress | 
PPE Storage Space | Value | 1. Identify capacity demand 2. Source premises 3. Capital Bid 4. Works & Commissioning | Sonny James / Mark Taylor | Identify suitable location and premises | Sonny James / Mark Taylor / Kathy Giles | Legal Team (Hempsons) | 3- 6 month (decision on approach) | Trustwide | in progress | 
Lease completions | Value | 1. Agree Heads of Terms 2. Agree red line drawings 3. Complete Leases | Sonny James/ John Brennan / Frank Riedel | Time constraints | Frank Riedel / John Brennan | Legal teams / Landlords | Qtr 4 | Trustwide | in progress | All leases at various stages of advancements with the respective landlords. Target date to sign all outstanding leases 25th March 2022
Create a new Estates net zero plan | Staff experience/population health/value/experience of health | 1. Creation of Plan (s) 2. Identification of funding 3. Regular reporting | Adam Toll/Mark Taylor | Funding. Accurate financials CDEL limitations | Estates | ICS Partners/External consultants | Qtr 2 | Trustwide | In progress | 
Pioneering decarbonisation pilot programme at Beech Close Resource Centre to fully decarbonise an existing site | Staff experience/population health/value/experience of health | 1. CPSG approval. 2. Funding approval 3, Tender and Appoint contractor | Adam Toll/Mark Taylor | Investment and local planning issues. CDEL limitations | Kathy Giles/Mark Taylor | External consultants/Local Council | Qtr 2 | Local/Place-based | In progress | 

## Slide 8
Estates Annual Plan Priorities 22-23
Key Priority Area | Strategic Priority (staff experience/population health/value/experience of care) | Milestones | Local Leads | Challenges | Internal Support Required | External/Corporate Support Required | Expected Delivery Dates + Timelines | Scale | Status | Comments
Identifying sites for onsite energy generation | Population health/value | 1. Sites audited and info updated to master site sheet | Adam Toll | Investment availability | Estates | ICS partners/External consultants | Qtr 2 | Trustwide | In progress | 
Identifying potential for combined energy purchasing or combined renewables | Population health/value | 1. Agreement with ICS / ICB partners | Adam Toll | Combined investment and red tape | Finance Dept | ICS Partners | Qtr 2 | Trustwide | In progress | 
Increase recycling provision to 70% of sites | Population health/value | 1. Sites identified. 2. Costings received | Jeffrey Sham/Lateef Omosanya | Stock availability | Facilities Team | None | Qtr 4 | Trustwide | In progress | 
Initiate a reuse scheme | Population health/value | 1. Identify contractor who can manage the service | Jeffrey Sham/Lateef Omosanya | Space for storing items | Facilities Team | None | Qtr 4 | Trustwide | In progress | 
Locate sites for NHS forest | Staff experience/population health/value/experience of health | 1. Sites audited and info updated to master NHS site sheet | Jeffrey Sham/Lateef Omosanya | Planning/Council issues/maintenance | Site leads/Grounds maintenance teams | Council/Finance | Qtr 3 | Trustwide | In progress |