## Slide 1: IAPT Annual Plan 2022-23

## Slide 2
Staff wellbeing, equality
System Development
Staff training & development
Improving Care delivery
Corporate Support
Recruitment & Workforce
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
To improve the quality of life for all we serve
Improve experience with subcontractors
Integrated Care
Digital Offers
Demand & Capacity
Co-location – GPs, Community and Voluntary Sector
Integration & interface with wider MH Pathway
Increase variety of therapies
Collaboration with other IAPT services (Trust & ICS)
Training for managers, complex cases & culturally-sensitive interventions
Appraisals and PDP planning
Supporting Flexible Working
IT, Estates & Phonelines
Automation products & system enhancement
Communications with service Users
Recruitment Strategy and Retention/Progression
Staff wellbeing initiatives – new ways of working, wellbeing champions, communications
Tackling Health Inequalities
Focus on equality in staff development & support

## Slide 3
Priority​ | Actions​ | Ownership​ | Timelines​ | Challenges​ | Support required (internal)​ | Support required (external)​
Corporate support ​ | Develop a clear plan for digital, estates, P&C culture around the key themes and challenges , IT ​ Review IT issues and equipment , replenish stock to meet needs of service​ Improvement plan for recruitment issues , processes ​ define timescales and support roles from corporate services ​ | DMT/Corporate Teams​ | 12 months​ | Staff not getting paid for bank work, (people participation), not having enough clinical space, recruitment delays, poor IT equipment​ | Establishing name leads, having a feedback loop to review progress, or project group​ | IT, Estates, P&C, ​
Development of new functions and IAPTUS​ | Develop a plan to improve the experience of IAPTUS and make it more user friendly ​ - Review SLA Mayden to include clauses in term of response​ Review features that would enable improvement in experience and prioritise for deployment​ Agree timeframes for implementation of quick wins​ around the feasibility of what can be achieved from IAPTUS​ | Alex​ | On-going​ | Poor experience​ | Project group​ | Clinical systems and CDD​
Staff well-being, recruitment and retention​ | Developing a people plan based on understanding underlying issues affecting staff;​ Valuing staff, recognising hard work,​ Offer flexibility Hybrid roles​ Utilise staff feedback to agree initiatives around wellbeing for each team​ Weekly wellbeing sessions​ Tackle recruitment challenges​ Creating the space for staff wellbeing ​ Reduce changes of PWPs into new roles​ Identify improvements in clinical model​ Reduce target burden​ | ACDs​ | 12 months​ | Roles are highly pressurised, staff feel stressed, roles are target driven​ | Team Leads​ | P&C​

## Slide 4
Priority​ | Actions​ | Ownership​ | Timelines​ | Challenges​ | Support required (internal)​ | Support required (external)​
Xyla – improving experience​ | Identifying alternative options to provide care , improve experience ​ Identify ways to improve areas of challenges​ Improve communication as a quick win​ Establish a review group​ | DMT​ | 6 months​ | Challenges with experience, its external could it be in house or alternatives, communication challenges and expectations can be different and confusing, staffing gaps​ | Project support​ | Xyla​
Maintaining patient focus and targets​ | Recognise we cant get rid of targets, but agree initiatives to reduce burden ​ - Scoping session organised linking to staff wellbeing work above​ | DMT​ | 12 months​ | Feels like business as usual, meeting targets but staff under pressure from targets – highly target driven. Not meeting target is a major issue but need to consider individual patient needs ​ | Team leads​ | Commissioners ​
Staff Development- understanding needs and equality in offering training​ | Developing a staff development plan for each roles​ Developing well-being​ Scoping equity for each role​ Agreeing protected times​ Agree what line manager support is available ​ | DMT​ | 12 Months​ | Not enough time to access, staff over-stretched, working extra hours. ​ | Team leads​ | P&C ​