## Slide 1: Newham Annual Plan 2022-23

## Slide 2
New Service Developments
Integrated Care, Partnerships & Coproduction
Service User Outcomes
Staff Wellbeing
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
To improve the quality of life for all we serve
Strategic Objectives
Secondary Drivers
22-23 Priorities
Test and develop our new community rehab approach in partnership with LBN – establish a Newham plan and Offer for rehab service users
Workforce, Equality and Diversity
Articulate staffing models and care intervention models – ensure service standards and SOP, Scope out opportunities in Newham
Test and develop an integrated approach to older adult mental health in primary care and enhance local authority interface across both inpatient and community settings – PCN, Inpatients, CMHT, Memory Workstreams in place, agree a plan for key outcomes
Stabilise community integrated mental health services such that enhanced primary care provision in resumed and outpatient care is transformed – assessing capacity and demand for new care pathways, move the “outpatient CIMHS – Integrating team with CRT
Meeting waiting list and access standards with partners and GP engagement plan/pathways mobilised
Streamline recruitment process – agree quick wins, identify initiatives around expediting visas
Focus on staff needs, cultural expectations, drivers of wellbeing, health, and support transition back to the workplace after sickness/illness
Develop manager skills and training to address health and wellbeing, focus on staff engagement and develop a structured approach to support managers
Develop relationships with Essex universities to promote ELFT vacancies and consider creative approaches to recruitment process to redesign vacant posts.
Develop a good model of collecting feedback from patients and encourage meaningful engagement/communication directly with service users
Increase referrals from former inpatients to PPL work – improve employment opportunities
Improving access and reducing inequalities – ASD and LD population – understand what is available for them and provide support.
Deliver on ambitions set by the Newham inpatient improvement plan – focus on safety and prevent future death notification, observations, practice, risk management, tranquilisation
Revive violence reduction work and develop a self-assurance and governance system to identify early warning signs to ensure proactive working
Enhance trauma informed care and develop clear structures and systems to manage increased complexity
Waste reduction
Redouble efforts in tackling inequalities and inequities in the systems we influence – understand impact e.g. access to services, understanding protected characteristics
Understand lived experience across workforce – ensure good representation across system, work with central team to ensure correct recording and improve functionality
Evaluate previous approach and expand further by prioritising intersectionality.
Value learning systems for QI projects
Digitally enabling service users and improving employment access work
Sustainability

## Slide 3
Newham Annual Plan Priorities 22-23
Priority | Actions | Ownership | Challenges | Timelines | Support Required (internal) | Support required (external)
Test and develop our new community rehab approach in partnership with LBN | Linking Trustwide work with Sheraz, Gina to support rehab plans Map/resources the current rehab offer across the Trust Scope out the opportunities in Newham Outcomes for residents Establish a Newham Plan and Offer for Rehab service users Staffing models and care/intervention models articulated Service standards and SOP | Gina/Michael/Fenno DMT for oversight | Housing issues, complex patients, delays in discharges, not enough community resources to manage need in the community, social care not being present, care home capacity | 12 months | Local DMT, project support | Wider partners in community, PCN, Local Authority
Test and develop a more integrated approach to older adult mental health in primary care and to enhance local authority interface across both inpatient and community settings | Workstreams currently in place (PCN, Inpatients, CMHT/memory) Agree plan for key outcomes and milestones for each | Fenno/Michael/Azad DMT for oversight |  | 12 months |  | 
Stabilise our community integrated mental health services such that enhanced primary care provision is resumed and outpatient care is transformed. | Assessing capacity and demand for new care pathways Move the “outpatient” cohort to CIMHS – integrating team with CRT Nursing and medical workforce stablisation Meeting waiting list and access standards Partners and GP engagement plan/pathways mobilised | Michael/Fenno/John DMT for oversight | Significant complexity in community transformation work, risks, getting pathways and resources in place, pressures on GP, |  | Ensure sufficient capacity in place | Digital, P&C, CDD. LA

## Slide 4
Priority | Actions | Ownership | Challenges | Timelines | Support Required (internal) | Support required (external)
Staff wellbeing – recruitment, estates, competencies | Develop a plan that: Builds on the current plans in place Agree quick wins (oyster cards, renumeration, benefits for staff) Streamline recruitment processes Identify initiatives around expediating visas Skills and training gap analysis Agreed plan of what DMT can do and what central support is required Consider if we can have a fixed period in Newham Linking with Trustwide workstream Staff engagement and linking to demographics Focus on staff needs and drivers of wellbeing in terms of lifestyle Focus on mind-set of health and wellbeing Development of Trialog Understanding staff cultural expectations Developing manager skills to address health and wellbeing – developing a structured approach Support for managers Support transition back to the workplace after sickness/illness Creative approaches to recruitment process – redesign vacant posts Develop relationships with Essex universities to promote ELFT vacancies. Over-recruitment Succession planning, early leadership development and exposure | Preeti/Bailey/Fenno/George/Ed DMT for overview People and Culture Recruitment | Recruitment and retention due to inner London weighting, being clear on what the plans are at the moment, attracting staff to Newham Don’t co-design issues staff experience Retention and constant re-training of staff for stability. Asset stripping due to staff upskilling Limited to London universities – competition for students among other trusts. London weighting | Ongoing | DMT leads People and Culture Finance QI Support | P&C Recruitment & Retention workstream Trust-central support Anchor organisations e.g. LBN Parameters of university relationships Resourcing team – using social media, ethical international recruitment
Newham Annual Plan Priorities 22-23

## Slide 5
Priority | Actions | Ownership | Challenges | Timelines | Support required (internal) | Support required (external)
PPL Priorities | Good model of collecting feedback from patients Increase referrals from former inpatients to PPL work Improving access and reducing inequalities – ASD and LD population – understand what is available for them and support Improving employment opportunities – education and healthy lifestyle QI Projects? Meaningful engagement -Communication directly with service users Agree plan for Newham from WTG Digitally enabling service users | Rose/Bailey DMT for oversight | Struggling to get a variety of voices | Ongoing | People Participation QI | Public Health – wider population work in terms of access and intelligence Health Watch Population Health (work stream)
Deliver on our ambitions set by the Newham inpatient improvement plan | Focus on safety – ensure patient safety (QI projects) Preventing future death notification – observations, practice, risk management, tranquilisation Self-assurance and governance system – early warning signs to ensure proactive working Link to staff wellbeing – revive violence reduction work Work in a trauma-informed way, respond to the needs timely Ensure practice is in line with new legislation Ensure restrictive practice in inpatient setting Clear structures and systems to manage increased complexity – physical health complexity | George/Marilyn/Gavin DMT for oversight | Increased complexity Engagement to a wider audience | Linked to different work-streams | QI Locally HR BP support - Preeti | Director of Nursing support OD and P&C – Donna
Newham Annual Plan Priorities 22-23

## Slide 6
Newham Annual Plan Priorities 22-23
Priority | Actions | Ownership | Challenges | Timelines | Support required (internal) | Support required (external)
Redouble our efforts in tackling inequalities and inequities in the systems we influence | Understand impact – e.g. access to services, understanding protected characteristics, improve data recording on population (staff + service users) – work with central team to ensure correct recording and improve functionality Held in Transformation Space and Improvement Plan Understand lived experience across workforce – ensure good representation across system Evaluate previous approach and expand further Importance of intersectionality – prioritise and focus Employment access work Focus on specific tasks | Preeti/Bailey DMT for oversight | Accessing staff data | Ongoing | Increase visibility Public Health colleagues QI support locally Mental Health Community Transformation | LBN Work-streams Local Authority Corporate governance team Clinical system team Developing transparent reporting/dashboards to New QI Workstream Population Health