## Slide 1: Tower Hamlets Mental Health Annual Plan 2022-23

## Slide 2
Digital Solutions
Integrated Care, Partnerships & Coproduction
Staff Experience and Wellbeing
New Service Developments
Estates
Improved Population Health Outcomes
Improved Experience of Care
Improved Value
Improved Staff Experience
To improve the quality of life for all we serve
Implementing the Community Mental Health Transformation Programme and develop offer for older adults
Improved access and flow
Embed PTS and Arts Therapy in the Neighbourhood team by focusing on complex emotional needs
Improve and sustain acute mental health inpatient care by reducing restrictive practices
Continue to manage beds in the service and continue with co-production with service users to focus on observation practice
Embedding trauma informed care in the service – design and deliver training co-produced with service users
Improve creative offer for staff development including training programmes, team development days and shadowing opportunities.
Aim to fully recruit into all posts and support secondment opportunities in the service
Ensure the wards are working to the Prevention of Future Deaths recommendations
Engage with VSCE to support delivery of inequalities agenda across TH services and use data to review these inequalities and support interventions (develop inequalities dashboard)
Have an understanding of capacity to share premises with local partners.
Improve offer for carers in the neighbourhood
Review current estates in line with added staffing across teams and create extra clinical capacity for clinical spaces within existing estates
Upgrade the inpatient facility to meet minimum requirement
Shape future services around digital options – conduct a scoping exercise for all digital options in service
Reduce inequalities and improve access to mental health and learning disability services and experience of all with protected characteristics
Embed Dialog+ in neighbourhood teams
Support staff induction to digital options while implementing patient knows best (PKB) across TH
Quality improvement to make trauma informed environments and develop borough-wide offers for trauma-informed working
Equality, Diversity and Inclusion
Support homeworking with appropriate technology and review experience of staff
Improve physical health care outcomes for service users with SMI and LD across TH – improve access and completion of annual health checks
Improve access to systems to request for physical health checks for ELFT clinicians (blood order/imaging)
Develop partnership working across NEL and new ways of working with CCG – co-produce governance systems and future patient safety incident reviews
Development of Physical Health HCAs to work with primary care to complete SMI and LD checks
Improve experience of carers through implementation of the carers strategy – improve identification and recognition of carers
Develop clearer pathways to access support for carers and help in crisis – ensure the right support is available for young carers and prioritise carer’s voice and involvement
Carer’s Strategy

## Slide 3
Key Priority Area | Strategic priority (population health, experience of care, staff experience, value) | Milestones | Local Leads | Challenges | Internal Support Required2 | External/Corporate Support Required | Expected Delivery Dates + Timelines
Improving staff experience, wellbeing and development opportunities in the service. | Experience of care | 1. Working through feedback in staff survey 2. Aim to fully recruit into All posts in the service 3. Explore staff development programme for managers in the service 5. Support secondments in services 6. Create Shadowing opportunities in the service 7. Encourage team development days across the year for all teams 8. Reflective practive across all teams | Day Njovana Sarah Dracas Marion Reilley Evah Marufu Preeti Basra | 1.Staff recruitment processes | 1. Clear recruitment support for managers , encouraging flexibility 2. Monitor hard to recruit posts and find alternatives. 3. Targerted Development/ support programme for leads in services 4. Discuss with leads secondments and apportunities to shadow 5. Staff support steer in all governance meetings | 1. People and Culture 2.Organisational Development 3. Recruitment advisor/ HR support to return to site running surgeries 4. Support to develop an programme for Leads in services | 18 months
Implementing the Community Mental Health Transformation programme | Experience of care | 1.Developing offer for Older Adults 2. Imbedding PTS and Arts Therapy in the Neighbourhood Teams 3. Focus on complex emotional needs offer 4. Offers for carers in Neighbourhood teams 5. Embedding Dialoge+ to replace CPA process across all neighbourhoods 6. Imbedding Digital offers as part of the transfomation of services | Marion Reilley Jammie Stafford Rebecca Rawding | 1. Engagement with partners 2. Shared Governance across different organisations 3. Staff Turnover 4. Slow process |  |  | 24 months
Improving and sustaining Acute Mental Health Inpatient Care. | Staff experience | 1. Work to reduce restrictive practices 2. Esuring the wards are working to the Prevention of Furtre Deaths recommendations 3. Continue to manage beds in the service 4. Increase co-production with service users in particular focus on observation practice 5. Work to improve experience of service users with suicidal and self harm worries | Evah Marufu Ferdi Johnson Marissa Bouman | 1. Developing data set for Restrictive practices training for staff 2. Out of area patients who are complex to discharge 3. Developing inpatient specific training for suicide and self harm |  |  | 12 Months

## Slide 4
Key Priority Area | Strategic priority (population health, experience of care, staff experience, value) | Milestones | Local Leads | Challenges | Internal Support Required2 | External/Corporate Support Required | Expected Delivery Dates + Timelines
Improving Estates within the service ​ | Experience of care​ | 1. Review current estates in line with added staffng across most teams​ ​ 2. Create extra capacity for clinical spaces within existing estates​ ​ 3. upgrade of inpatient facility to meet minimum requirement​ ​ 4. Understanding of capacity to share premises with local Partners​ ​ 5. Future planning of service to include consideration of impact on estates ​ | Day Njovana​ David Stevens​ Frank Riedel ​ | 1.Working with Barts Health to repurpose estates​ ​ 2. Funding for inpatient facilty upgrade​ ​ 3. Consideration of Covid and impact on estates ​ | 1. Leads of services ​ | 1. Estates Department ​ ​ | 12 Months​ ​
Imbedding Trauma Informed Care in the service ​ | Experience of care​ | 1. Designing and delivering training co-produced with service users​ ​ 2. Quality improvement to make trauma informed environments​ ​ 3.Developing Borough wide offers for Trauma informed working​ ​ | Steven Livingstone​ Evah Marufu​ Patricia Potter ​ | 1. Training Access​ ​ 2. co-production with other organisations - developing shared values ​ | ​ | ​ | 12 Months​ ​
Reducing Inequalities and improving access to mental heath and Learning Disability services and experience of all with protected characteristics. ​ | Experience of care​ | 1. Ensure we implement the inequalities report recommendations​ ​ 2. Engage with VSCE to support delivery of inequalities Agenda across Tower Hamlets services​ ​ 3. Using Data to review ineqaulities and support interventions across all services - Developing an inequalities dashboard​ ​ 4. Engaging Local residents in developing responses to inequalities​ ​ 5. Raising awareness and stigma of mental health and Learning Disability in local communities ​ | Day Njovana​ Marie - Michelle Mousse​ Marion Reiley​ Preeti Basra​ Sarah Dracass​ ​ | 1. Developing shared data sets that supports what matters to all groups​ ​ 2. Future Funding for work that is agreed to add value to the communities​ ​ ​ | ​ | ​ | 12 Months​ ​

## Slide 5
Key Priority Area | Strategic priority (population health, experience of care, staff experience, value) | Milestones | Local Leads | Challenges | Internal Support Required2 | External/Corporate Support Required | Expected Delivery Dates + Timelines
Shaping future services around digital options- ​ | Staff experience​ | 1. Scoping exercise for all digital options in service - whats works well​ ​ 2. Staff induction to digital options in the trust​ ​ 3. Improving experience of digital in the service - increase capacity and inter-operability with local partners​ ​ 4. Impelementing Patient Knows Best (PKB ) across Tower Hamlets​ ​ 5. Support homeworking with appropriate technology - review experience of staff.​ ​ | Day Njovana​ Selma Ali​ Jane Clutterbuck​ Benjamin Rossington​ Marissa Bouman ​ | 1. Capacity of IT services to support scoping exercise​ ​ 2. Working with partner organisations to upgrade our IT in their buildings​ ​ 3. Scoping systems that are shared across Tower Hamlets with system partners​ ​ 4. Some of the systems depend on external partners and might not be their priority ​ | ​ | ​ | 12 Months​ ​
Developing partnetrship working across NEL and new ways of working with CCG ​ | Value​ | 1. Defining quality and perfomance indicators for services​ ​ 2. Co-producing Governance systems and future Patient safety inciident reviews​ ​ 3. Colloborating in projects across the ICS / Trust / Tower Hamlets Together​ ​ 4. Understanding Future Landscape of NEL colloboration ​ | Day Njovana​ Sarah Dracas​ Shaun Last​ Justin Philips​ Carrie Kilpatrick​ Marion Reilley ​ | ​ | ​ | ​ | 12 Months​ ​
Improving Physcal health Care outcomes for Service users with SMI and LD across Tower Hamlets ​ | Experience of care​ | 1. Improving access and completion of annual health checks for LD and SMI population ​ ​ 2. Acess to systems to request for physical health Checks for ELFT Clinicians (blood order/ imaging)​ ​ 3. Development of Physical Health HCA's to work with Primary care to complete SMI and LD Checks ​ | Judith Littlejohn​ Sarah Dracass​ Rebecca Rawding ​ | ​ | 1. IT intergration of system to ELFT system​ 2. Access to primary care data for SMI and LD physical health checks for HCA ​ | 1. Access to Tquest ​ 2. IT support to work with Barts Health etc ​ | 24 months​ ​

## Slide 6
Key Priority Area | Strategic priority (population health, experience of care, staff experience, value) | Milestones | Local Leads | Challenges | Internal Support Required2 | External/Corporate Support Required | Expected Delivery Dates + Timelines
Improving experience of Carers in the service through implementation of the Carers strategy. ​​ | Experience of care​​ | 1. Improve Identification and Recognition of Carers​​ ​​ 2. Staff should be aware of carers and trained to engage with carers effectively​​ ​​ 3. Clear pathways to access support for carers and help in a crisis​​ ​​ 4. Carer Voice and Involvement​​ ​​ 5. Ensure right support is in place for young carers​​ ​​ | Steven Livingstone​​ Marion Reilley​​ Evah Marufu ​​ | ​​ | ​​ | ​​ | ​​