## Slide 1: Discharge Notification Project

## Slide 2
Project Overview
Project Start
July 2022
Scoping of issue and stakeholder feedback
August – September 2022
Options appraisal
October – December 2022
Development of new Hospital Discharge Form
January – March 2023
New shorter Hospital Discharge Form deployed
March 31st 2023
Stakeholder feedback
April – July 2023
Bi-weekly Trustwide learning forum
April – July 2023
Project End
August 2023
Project Milestones
An internal review has been completed of the 24-hour notification of discharge standard to ensure that we were closer to meeting the target and offered appropriate and timely support for our service users. This prepared us for the national move from sending discharge notifications to GPs within 48 hours to 24 hours. All directorates fell below the 95% national target and were not able to account for all discharge notifications because there were delays in local processes which caused bottlenecks across the pathway. After completed the review, we were able to identify and implement a number of improvements that have results in improvements in performance across the Trust.
Purpose & Objectives
To support the delivery of the 24-hour discharge notifications standards. As such a Trustwide project board was established to:
  Develop a unified process and solution to capture compliance of this standard for reporting
  Identify best practice by liaising with external partners to understand what processes are most efficient
  Organise training and supporting material to embed new practices.
  Support teams to enhance the quality of contacts with service users.
Risk
Description | Likelihood | Impact | Mitigating Actions
Patient safety | High | GPs not having access to timely information which can affect care planning and delivery | Performance reviews monitored locally and reports in place to support improvement. Establishment of Discharge Notification project board with membership from key areas including local and corporate performance, pharmacy, clinical directors, and digital

## Slide 3
“Had to go to A&E to get support”
“Be more inclusive, language barriers”
“Randomly discharged on weekend”
“Chaotic discharge”
“Had to chase for letter”
“Missing DLF delayed medications”
“Repeatedly fell through the cracks”
“Loss in trust and faith in staff”
“Not involving carer sufficiently”
“Did not get a discharge letter”
“Staff not listening”
“Poor communication”
“Lack of follow-through on agreed plans”
“Telephone check-in provided limited help”
“Felt unsafe on discharge”
“Felt rushed”
“Plan for discharge from B&B was unclear”
“Transition to community care was disjointed”
“Need more help navigating system”
“Relapsed”
“No accountability”
“Everything feels like a battle”
“More Pre-discharge conversations”
“Felt Abandoned”
“Appointments not organised in community”
Why this matters: Learning from service users
“Lack of community support ”
“Benefit from information leaflet post discharge”
Discharge Process
DLF Form
“Better advance planning with me”
“Staff too busy ”
“Format is good”
“Content written without service user voice”
“Wording can compound feeling stigmatised”
“Less jargon”
“Didn’t know about HTT”
“Not as well as staff think I am”
“Discharge letter is very helpful tool ”
“Staff should incorporate both professional and user perspective to reduce stigma”
“More detail about the follow-up plan so its clear who is responsible and by when”
“Letters don’t always get to GP electronically ”
“More opportunities to discuss this before discharge ”

## Slide 4
Why this matters: Service user experience
Video: 2 minutes watch time

## Slide 5
Key changes to the process
The Discharge Liaison Form in RiO has been redesigned to be shorter and more concise, resulting in fewer sections that clinicians need to complete.
1
2
The ‘Treatment and Progress Summary’ has been removed and the ‘Follow-up Plan’ section has been reorganised, resulting in clearer post-discharge guidance for GPs and community teams
3
The Trust Informatics team has developed new Power BI dashboards to help wards more closely monitor performance
4
The rounds of consultations with Junior Doctors, GPs and Service Users enabled the project group to clarify the purpose of the DLF. Service Users found the ‘My Recovery/Safety Plan’ are more informative document compared to the DLF that was clinical and lacked the voice of a service user

## Slide 6
Performance Highlights and Change Ideas
Change Ideas
Performance Highlights
The Trust has seen improvements in the average time taken for the DLF to be uploaded
Tower Hamlets has reduced the average time for the DLF to be uploaded by 58%
Tower Hamlets has improved their oversight and governance processes around the completion of the DLF
Newham has reduced the average time for the DLF to be uploaded by 35%
Newham have implemented a ward round template that allows them to capture key aspects of the service users admission prior to discharge and as a result are not completing the discharge letter at the point of discharge.
Across the Trust, daily reminders are being issued by admin staff on the wards to ensure that junior doctors are aware of any service user
Daily reminders for outstanding DLFs – reduced the backlog by over 60%
Ward round template to capture key aspects of service users admission prior to discharge
Establishment of clear oversight and governance to ensure doctor reviews the quality of the letter
Improve communication with service users prior to discharge through posters/leaflet
Establishment of MDT project group to improve ways of working
Broadening of Power BI displays on the wards to allow for better monitoring of performance
MDT ward huddles to support discharge planning
Local performance training with Junior Doctors and Pharmacy

## Slide 7
Doctor
Review Final DLF Letter
Pharmacy
Ward Nurse
Send to GP (local Lead)
The Junior doctor will complete the "Hospital Discharge" form.
Junior Doctor to ensure that all the information on the form is correct including admission and discharge date.
Ward pharmacist will validate the form and digitally sign. Please note that the pharmacist will just be reviewing medication and allergies.
Pharmacy will validate medication on the same day if received before 2pm.
Ward pharmacist will use editable letters to create the discharge liaison letter (see email below for guide on how to complete this)
Gold standard is a copy of discharge letter printed and given to patient
Patient to be given medication, which has been sense checked by Ward Nurse
Patient discharged
Depending on the borough the ward administrator, Pharmacist, or Doctor will send the discharge letter to the GP.
Please note, it is the Junior Doctors responsibility to check the final letter before it is sent to the GP and ensure all quality checks have been completed
Establish or follow existing governance process for reviewing final DLF letter. Use DLF Data Report to view contents of complete form.
Doctors are responsible for the quality and accuracy of the discharge letter prior to pharmacy sign off and/or admin sending to GP
Junior Doctor or the Consultant will email Pharmacy to notify pharmacy that their form is ready for validation
Recommended process flow
Prior to discharge (24 hours of earlier)
Send to Pharmacy by 2pm to validate same day
Share with service user and send to GP within 24 hours of discharge

## Slide 8: Tips and Guidance
Establish clear oversight and governance procedures to guarantee that the Junior Doctor reviews the quality of the discharge letter before it is sent to the GP
Implement a comprehensive discharge planning process to prevent the discharge letter from being completed at the end of the admission. Use MDT pre-discharge meetings to gather key information pertaining the service users admission for the discharge letter
Communicate with service users prior to discharge to ensure they are aware of what to expect and have the necessary contact information
Communicate the 72-hour follow-up plan clearly to the service users and relevant community team so that they are aware of what to expect after discharge
Service users have expressed the value of having documentation to take with them following discharge. The ‘My Recovery/Safety Care Plan’ document provides structure and guidance for their recovery in the community
Service users should be leaving the ward with a copy of their discharge letter, or if this is not possible, ensure a copy of the My Recovery/Safety Care Plan is provided on discharge