## Slide 1
Mental Health Law Department 2024/25 Annual Plan Priorities
Improved Population Health
Improved Experience of Care
Improved Staff Experience
Improved Value
Trust Strategic Objective
Priority areas for the service
Partnership, coproduction
New service development
Service user outcomes
Staff and service user wellbeing
Digital First
Access, Demand, Capacity
Workforce, equality, diversity
Estates
Bids and contracts, commissioning, value
Maintain support to Operations through existing MHL governance, strengthened MHA/MCA KPI reporting and improved frontline connection
Give the MCA function some stability in terms of resources and mission
Appoint new Associate Hospital Managers and improve timeliness of AHM Reviews
Strengthen MHL training strategy including local inductions
Further develop digital MHL solutions to support Operations and overall governance
Support MHLD frontline to deliver effective service (via training, clearer JDs/SOPs, better IT, resource deployment)
Strengthen MHL communication strategy
Re-introduce MHA and MCA audit cycles
Sign off MHA Admin SLAs with partner acute trusts
Defined workstreams / projects / programmes for 24-25
Annual plan for 2024-25: Team/service: Mental Health Law Department

## Slide 2
Priority/ Key Objective | What performance measures will be monitored? | How does this link to your FV/ Sustainability goals | What support is required to achieve this priority? | Accountable lead
Maintain support to Operations through existing MHL governance, strengthened MHA/MCA KPI reporting and improved frontline connection | MHLD represented at each of the 10 DMTs every quarter New MHA/MCA KPIs introduced Evidence of clear lines of communication established between frontline clinicians and frontline MHA offices | Better governance = decreased risk of legal challenge & legal costs = better FV | Operations | AD of MHL/MHL Managers
Give the MCA function some stability in terms of resources and mission | Stabilise MCA team staffing establishment Mission discussed and agreed with corporate ELFT partners (Legal Affairs and Safeguarding), partner acute trusts, LAs and ICBs | Decreased risk of legal challenge = better FV | HR Legal Affairs Safeguarding Partner acute trusts Partner local authorities ICBs | Deputy AD of MHL/MCA Manager
Appoint new Associate Hospital Managers and improve timeliness of AHM Reviews | AHM ToA located and revised with HR’s support New AHMs appointed 80% of AHM reviews held within 10 weeks of trigger | As above | HR | AD of MHL
Strengthen MHL training strategy including local inductions | MHL training strategy revised so as to include both corporate training provision and local training provision Receipt and acceptance of statutory documents training strategy agreed Strategy put in place to meet bespoke MCA training needs of specialist services | Local training = improved sustainability + FV | Medical Education Practice Development Nursing L&OD | AD of MHL Deputy AD of MHL MHL Managers
*quarterly milestones currently being agreed

## Slide 3
Priority/ Key Objective | What performance measures will be monitored? | How does this link to your FV/ Sustainability goals | What support is required to achieve this priority? | Accountable lead
Further develop digital MHL solutions to support Operations and overall governance | Thalamos version 2 successfully rolled out as part of eMHA project MHLD frontline confident with reporting incidents on InPhase MHLD Seniors confident with signing off and monitoring incidents on InPhase Operations confident using Power BI to monitor their MHA compliance Electronic MHL risk register in place | Digital solutions = improved sustainability | Digital Programme Management Governance & Risk department Informatics | AD of MHL
Support MHLD frontline to deliver effective service (via training, clearer JDs/SOPs, better IT, resource deployment) | Development pathways put in place to plug gaps in management skills, leadership skills and MHA/MCA knowledge JDs revised Further SoPs put in place Resources deployed effectively and fairly between localities | Decreased risk of legal challenge = better FV | L&OD HR | Senior Supervisors
Strengthen MHL communication strategy | Intranet Public facing website Newsletter Roadshows | As above | Communications | AD of MHL Deputy AD of MHL MHL Managers
Re-introduce MHA and MCA audit cycles | Audit cycle agreed by MHLMG Audits carried out as per agreed cycle | As above | Informatics | AD of MHL Deputy AD of MHL MHL Managers

## Slide 4
Priority/ Key Objective | What performance measures will be monitored? | How does this link to your FV/ Sustainability goals | What support is required to achieve this priority? | Accountable lead
Sign off MHA Admin SLAs with partner acute trusts | All 3 SLAs signed Invoices issued accordingly | Income generation = better FV | Contracts Finance | AD of MHL Deputy AD of MHL MHL Manager for MHA